## How to guide
Data Quality Action Plan
This document will help you plan all of the data quality tasks used in IPA. Follow the instructions below to complete your plan. Green sheets and columns should be edited by you. Blue sheets are formulated and you should generally avoid editing them
Your project name | Enter project name here
Step | Sheet | Required action
1 | DQAP template Box location | Create a copy of this template in your project’s Box folder. The file should remain a Google Sheets. DO NOT download it as an Excel file as this will ruin the conditional formatting.
2 | DataQuality_Tasks | Define which data quality tasks you are using and write a general description of what will be checked with each task. (Fill-in green columns) If there is any other data quality activity you are planning to implement, add them as new rows.
3 | DMS | Define which of the DMS checks are useful for your survey, mark the boxes for active checks and fill in the identified survey variables for your project. (Fill-in green columns) For this process, we encourage you to review the survey in full to be able to identify all of the required checks and not include unnecessary ones.
4 | Issues_Actions | Read through the Issues_Actions sheet. For a less cluttered view, manually filter column C with the active checks to see the issues that can be identified for your data collection. If there is an additional issue you would like to add, create new rows in this sheet. Also modify any action as you consider necessary.
5 | Issues_Actions | Confirm that the person responsible for each action corresponds with your project's staff assignment (Edit green columns) There are programming actions which are mainly back-end office actions, while field protocols action require actions with field staff. The assignment of responsibilities is only a suggestion and you can freely modify this column. You may also use the specific names for your team members.
6 | Summary | You're done! Now socialize this plan with the rest of your research team. The Summary sheet will promote communication and accountability with your Research Manager and Field Coordinator. If it is useful, share this plan with your PI. All the feedback you can get on this stage will guarantee that you prepare and program the best possible data quality activities and DMS.
7 | Your DMS | Finally, it is time to start programming your DMS. Remember that you can get started here

## Summary
Data quality tasks |  | DMS plan summary
Active data quality tasks | What is being checked with this task? | Active outputs | Variables identified for check | Inactive outputs

## DataQuality_Tasks
Activity | Description | How can this data quality activity help? | What does this data quality activity require? | Activity active in this project? | What will your project check with this activity? | Recommended resources
Benchtesting | Bench testing means testing your survey in the office with non-programming staff. Benchtesting is an iterative process wherein testers run the survey in different scenarios and provide feedback, while the programmer(s) make changes; note that even small changes to a survey must go through the bench testing process again, as it is easy to make mistakes that affect other parts of the survey. | Benchtesting will help you identify programming issues with wrong skip patterns, invalid constraints for answers, typing errors and many more. It will also help you identify issues related to survey design such as translation or unclear questions | Non-programming staff to support benchtesting At least 3 days (depending on survey length and complexity) to adjust the survey programming Programmers can also use the ipacheckscto Stata to validate common programming issues before benchtesting | No |  | Benchtesting manual ipacheckscto
Pilot | A pilot is intended to test the survey in a non-sample population with a limited sample size. In general, pilots are not used for generalizable knowledge but rather have the purpose of testing either the survey design or field and data protocols. | Pilot usefulness depends on the objective set by the PI and research team. I can be focused on testing the survey questions and translation or providing feedback on logistical and operational considerations to reach out respondents. See the Pilot manual for more detail on how a Pilot can be used and designed. | Piloting a survey requires sufficient time to make adjustments to survey design and programming or field protocols If the Pilot is collecting PII and will be used for generalizable knowledge, they will require IRB approval | No |  | Pilot manual
False Launch | A false launch is a simulated survey kickoff in a non-sample community without informing field staff it is not part of real sample. They should be conducted in locations that closely resemble the actual sample scenarios. | False launches are aimed at gaining insights into the execution of the initial survey day and improving preparations for real data collection | False launch requires communities that can be excluded from final sample | No |  | False launch manual
Soft Launch | Soft launch survey consists of a slow and a low scale sample survey launch for 1-3 days | Since a soft launch means easing into data collection activities, it can help you identify issues related to field, survey protocols and data flow Likewise, it is a great opportunity to re-train staff by providing feedback upon real survey implementation | Feedback mechanisms in place with field officers Supervision and accompaniments from field and research staff is highly encouraged during soft launch | No |  | Soft Launch manual
Spotchecks | Spotchecks consist of random (and more importantly unpredictable) visits by research staff to surveyors. It is key that this visits are unannounced to make sure surveyors are following survey protocols even without supervision. Spotchecks don't need to last for the complete duration of the survey. | Spotchecks are the ideal tool to make sure surveyors are following field survey protocols. For instance, carrying the required equipment, sticking to sampling strategy and surveying the correct research participants It is always a good sign if field officers are following protocols even without supervision | IPA’s standardized SurveyCTO spotcheck form Highly trained field or research staff availability to do spotchecks visits | No |  | Sample accompaniment and spotcheck form
Accompaniments | Accompanying refers to staying with surveyors and observing them conduct an interview. In the initial days of the survey, you should make sure that each surveyor is accompanied for the duration of the entire questionnaire to make sure that they understand the questionnaire correctly and can ask the questions with the required prompting. As the survey period matures, it is alright if the person accompanying the survey stays for 2-3 sections on each accompaniment. | Accompaniments are the best way to identify flaws in the way field officers are conducting the survey. It can help you make sure the consenting process follows the highest quality standards, that questions are being made correctly, answer options are read only when required and the data entries are made correctly, among many others. | Use IPA’s standardized SurveyCTO accompaniment form Highly trained field or research staff availability to do long duration accompaniments | No |  | Sample accompaniment and spotcheck form
HFC | High frequency checks consist of the Stata program “ipacheck”. This are user-written commands created and maintained by IPA. It follows a general format of three types of files: an input file, do-file, and output files. These files can be modified to fit your project. Each check will either have its own workbook or will be included on its own sheet in the HFC outputs workbook. HFC Outputs are displayed by observation/respondent, referencing each respondent id, enumerator, and variable that you need to see for that check. | If runned with a high frequency, they can help identify multiple issues from enumerator to programming errors. Its multiple checks are ideal to identify surveys that may require further scrutiny of audio recordings. For a detailed description on the functionality of each check, review the DMS tab in this file. | Read IPA’s DMS guide and HFC manual Set up and test the DMS Run frequently the DMS and review the Data Quality Action Plan for reference on issues that can be identified and the actions that should be implemented | No |  | HFC manual DMS github DMS wiki
Backchecks | A backcheck refers to when a highly qualified field officer (also known as a backchecker) visits (or re-contacts) a respondent a second time to re-administer a selection of questions from the original questionnaire. Those backcheck responses are then compared to the original responses. The bcstats program included in the DMS 4.0 helps you to identify discrepancies between answers, and thus to identify problems with your questionnaire (reliability of data), the field team, or both. Your quality action plan should have included a backcheck randomization plan, as well as an action plan for what to do when you encounter discrepancies. Other strategies when a re-contact is not possible, include a double entry of an in-person or phone survey or the double entry of the survey using an audio audit. | Backchecks are a great tool to identify data falsification. By re-contacting research participants you are making sure field officers did contact the correct participant. The set of questions included in the backcheck should help you identify cases when field officers didn't contact anyone or completed the survey with a different respondent. Likewise, included questions can help identify field officers making mistakes like typing errors or incorrectly classifying answers, among others. Finally, an additional benefit of back checks is that it reveals the robustness of the survey instrument. Re-asking questions can show how frequently the respondents change their answers. Usually, you want to be asking questions that are stable over short periods of time. If many respondents are changing their answers, you may need to revise your questionnaire in a follow-up, or add more rounds of surveying. For a detailed description on the functionality backchecks outputs, review the DMS tab in this file. | Read IPA’s backcheck manual, Design and programme a backcheck survey Discuss the backcheck survey PIs Set up the DMS 4.0 Highly trained field officers to conduct backcheck surveys | No |  | Backcheck manual

## DMS
Globals do-file section | Input file | Input sheet | Output file | Output sheet | Description | How can this information be used? | Check / Output active? | Survey variables and information for checks | Recommended resources
ipacheckversions | N/A | N/A | hfc output | outdated | Creates a list of submissions using outdated form versions | This check can help identify enumerators that are using outdated versions of the survey in their devices This is useful to flag surveys that were completed after substantial changes in the survey, which may require re-contacting participants or modifying variables | TRUE | formversion variable:
ipacheckids | N/A | N/A | hfc output | id duplicates | Displays the duplicate surveys in terms of surveyid | This can be used to identify duplicates in the surveyid caused by issues with case management or by enumerator resubmitting one survey multiple times | TRUE | surveyid variable:
ipacheckdups | N/A | N/A | hfc output | duplicates | Displays the surveys with duplicates in other key information for the survey (ID and phone numbers, GPS, etc.) This sheet finds duplicates based on the variables you provide. The rest of the checks won't work well if you have duplicates of the id variable, so those should be cleaned before running hfcs. This should be used for more subtle duplicates (i.e. GPS, phone numbers, etc.) | This check is useful as an alternative to identify duplicates or very similar participants. For instance, an enumerator may have surveyed the same participant multiple times or different family members from the same household while using different caseid's | TRUE | variables:
ipacheckmissing | N/A | N/A | hfc output | missing | Displays the percentage of missigness and # of distinct responses for the specified survey variables. It can be set to check all variables by specifying _all. Priority variables, if specified, will appear on-top of the table. | This can help identify survey programming problems for variables where you want no missing values such as ID variables. Inversely, this is useful to identify variables that are being omitted completely due to programming errors or overly restrictive relevance rules. Take into account that at the start of data collection, there may be many violations as the sample is to small to encounter all relevance cases. | FALSE
ipacheckoutliers | hfc_inputs | outliers | hfc output | outliers | This check verifies whether certain continuous variables contain outliers, where an outlier is defined to be a certain multiple of the IQR or SD | This helps flagging enumerator typing errors or data fraud in numerical variables which may need to be verified or corrected | FALSE | variable:
ipacheckconstraints | hfc_inputs | constraints | hfc output | constraints | This check verifies that continuous variables fall within soft and hard constraints. A soft constraint is a range that most values should fall within, but it is not logically impossible to encounter values outside this range (e.g. # of children 0 - 10). A hard constraint is a range that all values should fall within and anything outside is highly dubious (e.g. age 0 - 130). Hard constraints should also be programmed in SurveyCTO. NOTE: You should already be coding in constraints to your survey. If you have already entered a constraint in the xlsform, there is no need to include it here as well. | This information helps identifying potential enumerator typing errors. It is particularly useful if there are numeric variables that have narrow distributions and should have soft limits that you don't want to force as hard constraints in survey. For example, you expect participants to be within 18 and 30 years older but it is possible to encounter older people in the sample. | FALSE | variable, soft_limits, hard_limits variable, soft_limits, hard_limits
ipachecklogic | hfc_inputs | logic | hfc output | logic | This check verifies that skip patterns and survey logic are being obeyed. Patterns that are already enforced by the SurveyCTO form's programming do not need to be included | This check can help flag soft checks that should be confirmed by enumerators during the survey. For instance, a household that reports paying school fees but has no children. Strong incoherences in responses can also be used to flag surveys that may be fraudulent for further revisions by the research team | FALSE | variable: assertion:
ipacheckspecify | hfc_inputs | other_specify | hfc output | other specify | This check will help with categorical questions that include other category with the option for the respondent to identify their own category in a separate text box. This check lists the non-missing values for these specify other variables in the output file to facilitate recodes (a user specifies a value that matches one of the original categories) or re-categorizations (if many similar other values are encountered). This check has a complementary output sheet called "other specify (choices)" that displays the frequency for the variables that have an option to select "Other" (parent variables). This can help identifying the need to add another option to the choice list | This can be used during piloting or beginning of surveying to check if there is a common “other” response. This could allow you to add this answer to a choice list to avoid further cleaning of the “other” variable and hopefully lower rates of “other” choices. It can also help notice if there are some enumerators that need additional guidance or instructions on how to categorize in existing options | FALSE | parent variable: child variable:
ipacheckcomment | N/A | N/A | hfc output | field comments | This check imports, append and output all field comments in in dataset into the HFC output file Note: this output sheet is for the comments field type that allows enumerators to comment on questions outside of respondent answers, exported as a media file. If you have not included this is in your survey, this check will not work. | If included in the survey, this creates a neatly organized sheet consolidating field comments made by enumerators, which may provide additional context to some of the errors identified in other checks or may require an additional correction | FALSE | N/A. No specific variables required for this check
ipachecktextaudit | N/A | N/A | textaudit | fieldstats | Outputs stats for each of the survey fields duration. Only shows the stats specified in do-file for all of the field team. | This information is mainly useful to validate if some questions are usually taking longer or shorter than expected. This is particularly useful if there are some fields with priority in the survey for which duration needs to be monitored closely. For instance, consent fields or survey experiments | FALSE | N/A. No specific variables required for this check
ipachecktextaudit | N/A | N/A | textaudit | field average by enumerator | Calculates the average duration in each field per enumerator | If this information is cross-tabbed with the previous check, it is possible to identify if there is a particular enumerator that has shorter or longer than expected durations in specific fields | FALSE | N/A. No specific variables required for this check
ipachecktextaudit | N/A | N/A | textaudit | group stats | Calculates the average duration in each field for all of the field team | This check can help flag enumerators that have unusually short times in each groups which might pinpoint cases in which enumerators are not administering correctly the survey, cutting corners or not asking some sections of the questionnaire and falsifying data in the process | FALSE | N/A. No specific variables required for this check
ipachecktextaudit | N/A | N/A | textaudit | group average by enumerator | Calculates the average duration in each group for all of the field team | This information can be used as a reporting tool to RM or PI's as this shows the average survey duration and which groups are taking longer. It is particularly useful if there are big sections from the questionnaire that were programmed as groups that want to be monitored during piloting | FALSE | N/A. No specific variables required for this check
ipachecktimeuse | N/A | N/A | timeuse | timeuse by date | Creates a heatmap of most active hours during data collection for the starttime of the survey | This information can be used to monitor that enumerators are completing surveys during the expected time frames Additionally, it is useful to identify timeslots with generally high or low productivity | FALSE | N/A. No specific variables required for this check
ipachecktimeuse | N/A | N/A | timeuse | timeuse by enumerator | Creates a heatmap of most active hours for each of the enumerators for the starttime of the survey | This information can be used to monitor that enumerators are completing surveys during the expected time frames | FALSE | N/A. No specific variables required for this check
ipachecksurveydb | N/A | N/A | surveydb | summary | Creates a dashboard like summary to track general survey performance in terms of total submissions, % of missigness, duration, etc. | This dashboard can assist with reporting to PI's, RM or other partners as it presents a summary of the survey in a neat dashboard. It can also help log data collection process if the DMS is runned consistently | FALSE | N/A. No specific variables required for this check
ipachecksurveydb | N/A | N/A | surveydb | summary (grouped) | Tracking summary per key survey groups (different locations, localities, municipalities, etc.) containing the following information # of submissions % of consent % of missing of all variables % of don't know (% of non-missing) % of refusals (% of non-missing) % of other (% of non-missing) Survey duration stats (min, mean, median, max) # of form versions First and last date of submissions # of active working days | This output is similar in structure to the summary created for enumerators It is mainly useful if the survey has relevant survey groups and can allow to identify issues such as locations with low consenting or high % of missingness | FALSE | group variable:
ipachecksurveydb | N/A | N/A | surveydb | weekly productivity | Tracking periodical data of completed surveys. This data can be displayed with a daily, weekly and monthly interval by setting the option in the globals do-file | This output will help track the productivity and identify risks of not meeting the goals | FALSE | N/A. No specific variables required for this check
ipachecksurveydb | N/A | N/A | surveydb | weekly productivity (grouped) | Tracking data of completed surveys per key survey groups (different locations, localities, municipalities, etc.). This data can be displayed with a daily, weekly and monthly interval by setting the option in the globals do-file | This information is useful if the survey has relevant survey groups and will help track the productivity goals for this groups | FALSE | group variable:
ipacheckenumdb | N/A | N/A | enumdb | summary | Creates a summary table per enumerator with the following information for all of the submissions: # of submissions completed (count) % of missing of all variables % of don't know (% of non-missing) % of refusals (% of non-missing) % of other (% of non-missing) Survey duration stats (min, mean, median, max) # of form versions First and last date of submissions # of active working days | This can be used as information to identify enumerators that may need re-training or additional supervision or backchecking due to poor performance, mistakes or fraud. Multiple issues can be identified with this data. Firstly, this check will flag enumerators that comparatively to the rest of the team have high % of DK, Refusals or Other Second, it will help with identifying enumerators with low general productivity in relation to workdays Thirdly, this sheet can flag enumerators with shorter or longer surveys comparatively to the rest of the team or than expected | FALSE | enumerator variable:
ipacheckenumdb | N/A | N/A | enumdb | summary (team) | Same as the enumerator summary but aggregate per enumerator team | Similar to the previous output, this information will help flag problems within enumerator teams, which may be caused by errors from supervisors | FALSE | team variable:
ipacheckenumdb | N/A | N/A | enumdb | weekly productivity | Tracking data of completed surveys per enumerator for each of data collection weeks | This tracking data will help flag enumerators with low productivity or unusually high productivity | FALSE | N/A. No specific variables required for this check
ipacheckenumdb | N/A | N/A | enumdb | weekly productivity (teams) | Tracking data of completed surveys per enumerator team for each of data collection weeks | Similar to the previous output, this information will help flag teams with low productivity or unusually high productivity | FALSE | team variable:
ipacheckenumdb | hfc_inputs | enumstats | enumdb | enumstats | This output calculates stats for key survey variables per enumerator including: count of non-missing stats (min, mean, median, max) | This check is mainly used to monitor numerical or outcome questions in the survey where enumerators can easily manipulate responses. With a large sample, it is to be expected that these variables have similar stats across all of the enumerators. Alternatively, the count of non-missing can pinpoint enumerators that are intentionally using skip patterns to make surveys shorters. This check can be used for variables that go after a big skip pattern. | FALSE | key survey variables:
ipatracksurvey | N/A | N/A | tracking | tracking | Compares master/tracking data and survey datasets to create a progress report of survey completion rates | This can be used to track the progress on completition rates for the survey traget | FALSE
ipatracksurvey | N/A | N/A | bctracking | bctracking | Compares master/tracking data and backcheck datasets to create a progress report of survey completion rates | This can be used to track the progress on completition rates for the backcheck traget | FALSE
ipabcstats | N/A | N/A | hfc output | BC id duplicated | Identifies duplicates in terms of caseid for backcheck surveys | This can be used to verify surveys that potentially were backchecked multiple times | FALSE | N/A. No specific variables required for this check
ipabcstats | N/A | N/A | bc_comparison | Summary | Creates a dashboard summary of backchecks and error rates per type of error including: -Backcheck rate -Average days between survey and backcheck -Graph with weekly error rates | This information is useful as a reporting tool to RM and PI's as it gives an overview of the backcheck progress and results. It can also be used to identify adjustments required to accomplish backcheck rates or error rates that are not improving over time | FALSE | Type 1 variables: Type 2 variables: Type 3 variables: | Backcheck manual
ipabcstats | N/A | N/A | bc_comparison | IDs | This sheet flags the surveys with over a specified % of differences. You can set this % in the corresponding do-file section | The surveys flagged for high difference rate are potentially fraudulent, particularly if differences come from type 1 questions, or point out to significant enumerator mistakes | FALSE |  | Backcheck manual
ipabcstats | N/A | N/A | bc_comparison | comparison | Outputs a detailed list of all of the differences between survey and backcheck data | The way the information from this and the following sheets from bc_comparison is used, should be adapted to each specific project. You should consider if audio recordings are available, if you are doing audio audit vs. backchecks, the type of question, the study population and the moment in which backchecks take place, among others. Please refer to the backcheck manual. Some of the possible uses are the following: -For questions that shouldn't change between survey and backcheck (type 1 questions), differences are a red flag for potentially fraudulent surveys or enumerator/bakchecker mistakes. -If means for verification are available, such as audio recordings, reviewing the audio can help confirm specific actions such as replacing information, dropping a survey or re-training field staff. -If means for verification are not available, this information can be used together with the enumerator and backchecker tabs to check if they are making mistakes | FALSE |  | Backcheck manual
ipabcstats | N/A | N/A | bc_comparison | enumerator stats | Creates a dashboard of enumerator stats with percentages of differences for the 3 error types and all of the backchecked variables. Also displays the % of backchecked surveys per enumerator. | This information allows to identify enumerators that have relatively higher error rates per type of question. Generally, enumerators with relatively higher error rates are making mistakes and should be re-trained or have higher supervision and monitoring. | FALSE |  | Backcheck manual
ipabcstats | N/A | N/A | bc_comparison | backchecker stats | Similar to the enumerator stats, creates a dashboard of differences per backchecker for the 3 error types and all of the backchecked variables | This information allows to identify backcheckers that have relatively higher error rates per type of question. Generally, if there is a backchecker with relatively higher error rates, they are probably making mistakes and should be re-trained and monitored. | FALSE |  | Backcheck manual
ipabcstats | N/A | N/A | bc_comparison | variable stats | For the specified variables in the input, this sheet show the total backchecked questions and the error rate for all of the backchecked surveys. It also includes the following: -For numeric responses, this sheet shows the mean comparison test. -For error type 3 variables, it shows the reliability test. | This sheet allows you to analyse if some of the questions have higher error rates than others. For type 1 questions, once again high error rates can be a red flag for enumerator mistakes For type 2 questions, this information can be useful to identify problems related to the questions such as difficult to understand or long questions. Alternatively, it can help notice if the enumerators or backcheckers are not following survey protocols For type 3 questions, statistical differences can flag stability problems for outcome variables. The reliability test can be used to determine how stable are the outcomes across time and interviewer and identify the need for survey modifications or add additional rounds of surveying. Ratios greater than 0.8 are considered "high", while lower than 0.5 are a red flag for outcome measurements. | FALSE |  | Backcheck manual

## Issues_Actions
Issues |  | Checks |  |  |  | Programming actions |  |  | Field protocols actions
Source of issue | Issue description | Check active? | Data Quality Activity | Specific check / output | Relevant resources | Suggested action | Action description | Responsible for action | Suggested action | Action description | Responsible for action
Questionnaire issue | Programming issue in the appearance or relevance of questions, making a section or question not appearing when it should do | FALSE | Benchtesting | N/A |  | Update survey programming | Correct survey relevance patterns |  | N/A
Questionnaire issue | Translations questions have a different meaning than the original questions. |  | Benchtesting | N/A | Benchtesting manual | Modify question | Correct the translation. A backtranslation is encouraged to check meaning hasn't been changed |  | N/A
Questionnaire issue | Lack of constraints enable FO to skip and finalize the survey without answering a question |  | Benchtesting | N/A |  | Update survey programming | Required field should be updated in the survey |  | N/A
Questionnaire issue | Lack of constraints or inadequate ones allow FO to enter irrelevant or incoherent values |  | Pilot | N/A |  | Update survey programming | Constraint fields should be updated |  | N/A
Questionnaire issue | Survey options are not comprehensive, and FO are forced to choose "other,specify" | FALSE | Pilot | N/A |  | Update survey programming | Update answer options based on pilot answers and feedback |  | N/A
Questionnaire issue | Questions are not clear and answers are misleading |  | Pilot | N/A |  | Modify question | Review with PI the unclear questions |  | N/A
Research team issue | Survey durations are longer than planned | FALSE | Pilot | N/A |  | Consult with PIs | Consult with PI to determine a way to reduce survey lenght |  | Modify field logistics | Check daily productivity goals based on new information on survey length
Enumerator issue | FO are not following survey instructions or are phrasing questions incorrecly | FALSE | False Launch / Soft Launch | N/A |  | N/A |  |  | Re-train field staff | Re-traing FO's making these mistakes or give a general feedback session
Research team issue | Planned field logistics do not meet expectations for what is observable in the field | FALSE | False Launch / Soft Launch | N/A |  | N/A |  |  | Modify field logistics | Update field logistics to meet the challenges observed in the field
Research team issue | Data flow issues cause problems with data download, encryption or DMS programming | FALSE | False Launch / Soft Launch | N/A |  | Update survey programming | Correct any programming that causes issues in the data flow |  | N/A
Enumerator issue | FO are not following survey instructions or are phrasing questions incorrecly | FALSE | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO wrongly choses categories |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO does not probe enough in case of illogic answers |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO does not understand categories and records answers incorrectly |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO does not probe enough in case of “don’t know” |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO does not read answers when supposed to |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO does not insist on recording GPS (when not mandatory) |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO gives unnecessary examples |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO doesn't read consent form textually or doesn't allow sufficient time for questions |  | Accompaniments | N/A |  | N/A |  |  | Re-train field staff | First, register this issue in the accompaniment form. If it is a first instance, you can re-train the FO's making this mistake. If it's recurrent, consider a warning or dismissal
Enumerator issue | FO omitted completely the consent form |  | Accompaniments | N/A |  | Drop survey | Following research ethical standards, surveys without an explicit consent should be dropped. If the consent protocol was completely omitted, drop the survey. |  | Give warning to FO | If it is possible, interrupt the survey and make the necessary adjustments to read the consent protocol. Also, consider warning or dismissing FO. It is critical that enumerators follow strictly research ethical standards and omitting completely the consent form is considered a serious fault
Enumerator issue | FO submitted a survey two times for the same ID |  | HFC | id duplicates |  | Drop survey | First confirm which survey is valid and drop the duplicate if it is confirmed as not a valid survey. In case it is valid, correct the caseid |  | Give warning to FO | This might be cause for concern if one of the duplicates can be confirmed as fraudulent
Enumerator issue | An enumerator completes a survey using an outdated version after substantial changes |  | HFC | outdated |  | Consult with PIs | You should consult the PI to determine if it is necessary or not to re-contact the participant to recover unasked questions, or if you should drop the survey |  | Reconfigure devices | As soon as possible update the survey in the devices. Don't allow additional submissions from this enumerators.
Enumerator issue | Duplicates in other key survey variables. Enumerator has surveyed similar participants using different IDs. For example, they surveyed the same participant multiple times or different family members from the same household, when they shouldn't have. |  | HFC | duplicates |  | Drop survey | Fraudulent surveys should be completely dropped from sample. Confirm if original participant was contacted |  | Give warning to FO | This is considered a serious fault in case the survey was fraudulent
Questionnaire issue | Wrong relevance or skip patterns |  | HFC | missing |  | Update survey programming | Relevance fields should be adjusted in survey programming |  | N/A
Enumerator issue | FO registers outliers in data caused by typing errors |  | HFC | outliers |  | Replace incorrect values using corrections log | If you can confirm it was an error, replace this data |  | Re-train field staff | FO should be re-trained on how to avoid typing errors. If this error is more frequent, consider a warning.
Questionnaire issue | The respondent gives contradictory answers |  | HFC | logic |  | Update survey programming | If the survey shouldn't allow this contradictory answers, additional constraints can be added |  | N/A
Enumerator issue | FO types "other, specify" options when they could have classified in existing option |  | HFC | other specify |  | Recode "other,specify" options | These "other" answer can be re-categorized in existing options using replacement log |  | Re-train field staff | FO should be re-trained in how they should have classified their answer. Using specific examples is encouraged
Questionnaire issue | There is a common “other” response that was not included in the original survey |  | HFC | other specify |  | Update survey programming | If the frequency of this option is high, it can be added to the survey and values can be recoded to this new option |  | Re-train field staff | Explain the field staff about the changes
Enumerator issue | "Other specify" answers don't make sense or don't answer the question |  | HFC | other specify |  | Consult with PIs | If necessary, re-contact or re-visit participant to recover the information |  | Re-train field staff | FO should be re-trained in how they should have typed their answer. Using specific examples is encouraged
Enumerator issue | Enumerator includes as a field comment typing error |  | HFC | field comments |  | Replace incorrect values using corrections log | Use replacement log to include the correction |  | N/A
Research team issue | Productivity goals are not met |  | HFC | weekly productivity |  | N/A |  |  | Modify field logistics | Evaluate alternative adjustments that can boost productivity
Research team issue | Productivity goals for some locations are not met |  | HFC | weekly productivity (grouped) |  | N/A |  |  | Modify field logistics | Evaluate alternative adjustments that can boost productivity in the locations that have low productivity
Enumerator issue | FO rushing the survey |  | HFC | group average by enumerator |  | N/A |  |  | Give warning to FO | This is considered a serious fault. If possible, you should also confirm if the participant should be re-contacted
Research team issue | Productivity is low for some hours |  | HFC | timeuse by date |  | N/A |  |  | Modify field logistics | Evaluate if changes to enumerator scheduling are required
Enumerator issue | Enumerator completes survey outside of expected hours |  | HFC | timeuse by enumerator |  | Confirm if survey is fraudulent | You should confirm with field coordinator if there are reasons for this delayed submission |  | Give warning to FO | Normally, surveys shouldn't be submitted outside of expected working hours
Enumerator issue | Survey falsified as FO made a submission without having respondent |  | Backchecks | comparison | Backcheck manual | Drop survey | Fraudulent surveys should be completely dropped from sample. Confirm if original participant was contacted. In case they weren't contacted, consult with PIs if they should be included in the sample |  | Dismissal of FO | This is considered a serious fault and should result in the FO being dismissed
Enumerator issue | FO cutting corners or taking advantage of skip patterns to finish survey faster |  | Backchecks | enumerator stats | Backcheck manual | Consult with PIs | You should consult the PI to determine if it is possible to re-contact the participant to recover unasked questions or if you should drop the survey |  | Give warning to FO | As a first measure you should consider warning the enumerator but it is important that further investigation is made to determine if this behaviour occurred in other surveys
Enumerator issue | One FO has relatively higher errors in backcheck data for type 1 or type 2 errors |  | Backchecks | enumerator stats | Backcheck manual | Consult with PIs | Consult with PIs if you should modify some responses or if it is necessary to drop the survey. In any case, you should only change responses if you have means of verification such as complete audio recordings |  | Re-train field staff | This issue most probably flags mistakes made by the FO. Re-train them as a first measure and if repetitive consider a warning or dismissal
Enumerator issue | One Backchecker has relatively higher errors in backcheck data |  | Backchecks | backchecker stats | Backcheck manual | N/A |  |  | Re-train field staff | This issue most probably flags mistakes made by either the backchecker or the enumerator team they are backchecking. Try to identify who needs to be re-trained by using audio recordings.
Questionnaire issue | High type error 3 or low stability measures for outcome variables |  | Backchecks | variable stats | Backcheck manual | Consult with PIs | You should show this information to PI's and they can decide if there is need to modify the survey or do additional rounds of data collection |  | N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
Note on K26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @crodriguez@poverty-action.org han considerado auditar al auditor si presenta x% de errores? Assigned to crodriguez@poverty-action.org Reply: Sí, esa es la idea de esta acción. Pero no podemos definir un % generalizable porque ese porcentaje siempre es relativo
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Este issue type es de protocolos. Si consideran agregar más casos, el formato de spotchecks contiene los protocolos que cualquier proyecto debería seguir. Lo puedes consultar acá https://ipastorage.box.com/s/dvadjcfaf09de6hls07wpdwjw7ew5hga Reply: Entiendo. Pero acá no pusimos protocolos para hacer más clara la diferencia entre problemas logísticos y de desempeño del encuestador. Reply: Gracias por el recurso. Lo revisé para verificar que en errores grandes no se nos escapara ninguno.

## Lists (No edit) (hidden)
Programming actions |  | Field protocols
Actions | Responsible | Actions | Responsible
N/A | N/A | N/A | N/A
Reconfigure devices | Field coordinator | Reconfigure devices | RA
Update survey programming | RA/Analyst | Re-train field staff | RA
Drop survey | RA/Analyst | Revisit or recontact participant | Field coordinator
Replace incorrect values using corrections log | RA/Analyst | Warning | Field coordinator
Modify question | RA/Analyst - PI | Dismissal | Field coordinator
Recode "other,specify" options | RA/Analyst | Prioritize supervision | Field coordinator
Confirm if survey is fraudulent | RA/Analyst | Modify field logistics | Field coordinator
Consult with PIs | RA